## Feuil1
Makerhub Risk Register
Classification: Confidential
[8 empty] | Original Risk | [7 empty] | Residual Risk
Ref | External Ref | Risk Description | Asset | Asset Owner | Threat | Vulnerability | NIS 2 | Existing Control | Impact | Likelihood | Risk Score | Risk Rating | Risk Treatment | Treatment Plan | Open / Closed | New Control | Impact | Likelihood | Risk Score | Risk Rating
1 | Risk 1 | Unauthorized access to internal networks from the Internet | Firewall |  | Unauthorized access from the Internet | Overly permissive firewall rules | Article 21, 2.a | None in place | 4 | 4 | 16 | Major | Risk Reduction | Reduced exposure of internal networks through strict traffic filtering | Closed | The current control is effective | 1 | 1 | 1 | Minor
2 | Risk 2 | Malicious traffic entering the internal network without detection | Firewall |  | Malicious traffic exploitation | Absence of advanced traffic inspection (IPS/IDS) | Article 21, 2.c | None in place | 4 | 4 | 16 | Major | Risk Reduction | Improved detection and blocking of malicious network traffic | Open | SIEM and IPS implemented | 1 | 1 | 1 | Minor
3 | Risk 3 | Connection of unauthorized devices to the internal network | Access Switch |  | Unauthorized device connection | Lack of identity-based network access control (802.1X) | Article 21, 2.b | None in place | 3 | 3 | 9 | Moderate | Risk Reduction | Enforced authentication of devices before network access | Closed | The new control is effective | 1 | 1 | 1 | Minor
4 | Risk 4 | Late or non-existent detection of a security incident | Logging & Monitoring Capability |  | Late incident detection | Absence of SIEM and log correlation | Article 21, 2.d | None in place | 4 | 4 | 16 | Major | Risk Reduction | Centralized visibility and real-time incident detection | Closed | The new control is effective | 1 | 1 | 1 | Minor
5 | Risk 5 | Poor incident handling leading to increased impact | Incident Response Capability |  | Ineffective incident response | Absence of formal incident management procedures and CSIRT | Article 21, 2.e | None in place | 5 | 4 | 20 | Critical | Risk Reduction | Structured and coordinated incident response | Open | Hire a CSIRT Team | 3 | 2 | 6 | Moderate
6 | Risk 6 | Inconsistent or delayed decision-making during incidents | Cybersecurity Governance |  | Lack of cybersecurity oversight | Absence of a formal governance framework | Article 20 | None in place | 3 | 3 | 9 | Moderate | Risk Reduction | Clear roles, responsibilities, and decision-making processes | Open | Hire a GRC consultant | 1 | 1 | 1 | Minor
[9 empty] | 1 | 1
[11 empty] | Dashboard Summary | [7 empty] | Dashboard Summary
[11 empty] | Number Minor | 0 | 0 |  | 3 |  |  |  | Number Minor | 5
[11 empty] | Number Moderate | 2 | 6 |  | 3 |  |  |  | Number Moderate | 1
[11 empty] | Number Major | 3 | 0 |  | 6 |  |  |  | Number Major | 0
[11 empty] | Number Critical | 1 | 0 | [5 empty] | Number Critical | 0

## Feuil2
Risk Scoring
| Likelihood |  |  |  | Impact
| Likelihood | Grading | Description |  | Impact | Grading | Description
| Highly Probable | 5 | Likely to happen within the next month |  | Very High | 5 | Legal or regulatory compliance issue or breach System downtime in breach of agreed SLA’s, leading to contract loss. Impact on health or safety or individuals.
| Probable | 4 | Likely to happen within the next 6 months | x | High | 4 | Exposure of sensitive information to a non-authorised third party, system downtime, data corruption, impacting upon ability to deliver service (breaching agreed SLA’s)
| Possible | 3 | Likely to happen once within the next 2 years |  | Medium | 3 | Internal exposure of sensitive information beyond authorised individuals, system downtime, or data corruption with minor disruption to customer service (within agreed SLA’s)
| Unlikely | 2 | Likely to happen once within the next 5 years |  | Low | 2 | Detected security incident with no direct impact on operations or exposure to information
| Rare | 1 | Highly unlikely to occur - Less than once in the next 10 years |  | Very Low | 1 | No perceived impact
Risk Classification and Risk Treatment Default
| Risk Classification | Grading | Description
| Critical | 16 >= | Reduce risk
CEO authority required to accept risk at this level.
| Major | 10 - 15 | Reduce risk
= |  |  | Management Review Team authority required to accept risk at this level.
| Moderate | 5 - 9 | Reduce risk
Management Review Team authority required to accept risk at this level.
| Minor | 1 - 4 | Accept Risk